## Executive Risk Summary
Carmerek Labs (Carmerek X SaaS): Third-Party Risk Assessment, Items for Senior Management Escalation
Supplier | Carmerek Labs: "Carmerek X" SaaS for scientific data analysis
Data in scope | Carmerek's confidential intellectual property (scientific research data)
Supplier criticality | High: business-critical research tool processing crown-jewel IP
Overall residual risk | HIGH
Assessment basis | TPRM questionnaire, 15 questions; evidence provided and assumed sufficient
Assessment date | 28 October 2026
Recommendation | Escalate. Continue use only under a formal risk acceptance by the business owner, with a time-bound remediation plan agreed with Horizon Labs, contract security clauses, and Carmerek's-side compensating controls. Do not expand data shared or new use cases until Critical items are closed.
# | Key risk item | Related Qs | Rating | Why it matters to Carmerek's | Required action from Carmerek Labs | Carmerek's action / owner | Target
1 | No access control governance: no RBAC, no least privilege, no segregation of duties, no access reviews | Q10–Q13 | Critical | Anyone at Horizon Labs may be able to view, copy or alter Carmerek's IP, and nobody would know. Highest likelihood route to IP theft (insider or compromised account). | Implement RBAC and least privilege for Horizon X and its database; separate dev/admin/production duties; quarterly access reviews with evidence; restrict and log access to Carmerek's tenant/data. | Procurement + CISO: add contractual access-control requirements. Business owner: confirm which staff at Horizon can access Carmerek's data. | 90 days
2 | No security detection, monitoring or incident response capability | Q7, Q8 | High | A breach of Carmerek's data could go undetected, and Carmerek's may not be told in time to meet its own regulatory and contractual notification duties. | Centralised logging and alerting for application, database and identity; documented IR plan; contractual breach notification to Carmerek's within 24–48 hours. | Legal: add breach-notification and cooperation clauses. CISO: add Horizon Labs to Carmerek's IR plan third-party contacts. | 90 days
3 | No vulnerability management and no penetration testing of an internet-facing SaaS | Q5, Q6 | High | Known vulnerabilities in the app, Oracle DB or libraries could be exploited without Horizon knowing. No independent proof the platform or tenant separation is secure. | Deploy authenticated vulnerability scanning with defined patch SLAs (e.g. Critical ≤14 days); independent application and infrastructure pen test, then annually; share executive summary and remediation evidence. | CISO: review pen test report and track findings to closure. | 120 days
4 | No security framework or independent assurance | Q4 | High | No assurance that controls are designed or operating consistently; Carmerek's must rely solely on self-reported answers. | Adopt a recognized framework (ISO 27001 or SOC 2) with a roadmap to certification/attestation; appoint a named security owner. | Procurement: right-to-audit clause; annual reassessment. | 12 months (roadmap in 90 days)
5 | No DLP; backups mistaken for data protection | Q15 | High | Nothing prevents or detects Carmerek's IP leaving Carmerek Labs. Backups protect availability only, and their security and restore testing are unknown. | Implement DLP / egress controls on endpoints, email and cloud storage handling Carmerek's data; encrypt and test backups; confirm data location. | Business owner: minimize and, where possible, de-identify data sent to Horizon X. | 6 months
6 | Encryption claims unverified and incomplete | Q3 | Medium | Oracle encryption at rest may not actually be enabled; encryption in transit and key management are not described. | Provide evidence of TDE (or equivalent) enabled, TLS 1.2+ in transit, encrypted backups, and key management/access controls. | CISO: verify evidence. | 30 days
7 | Security awareness only at onboarding | Q14 | Medium | Phishing and human error remain likely entry points; awareness decays without refresher training. | Annual refresher training, phishing simulations, and secure-development training for engineers. | Verify at reassessment. | 6 months
8 | No dedicated security contact; contact data inconsistency | Q1 | Low | Delays and confusion during an incident; email address does not match contact name. | Name a security contact and deputy; confirm correct contact details. | Vendor manager: update supplier record. | 30 days
Positive finding | MFA is in place via Okta (Q9). Confirm it covers administrators, database and remote access.
Decisions requested from senior management
1. Accept the HIGH residual risk temporarily (business owner signs risk acceptance), or pause / replace the supplier.
2. Approve contract amendments: security schedule, breach notification within 24–48 hours, right to audit, data return and deletion on exit.
3. Require Carmerek Labs to deliver a remediation plan within 30 days, with Critical items closed within 90 days.
4. Approve Carmerek's compensating controls: minimize and de-identify data shared, SSO from Carmerek's identity provider if supported, and an exit plan for an alternative supplier.
5. Reassess CarmerekLabs in 6 months and record this supplier risk in the enterprise risk register.
Rating scale
Critical | Immediate exposure of Carmerek's IP; act now
High | Significant control gap; remediate within 90–120 days
Medium | Control partially in place; remediate within 6 months
Low | Minor gap or administrative issue
Info | Context only

## TPRM Questionnaire
Carmerek’s Thrid Party Risk Assessment Lab
Number | Question | Answer | Comment | Evidence | Risk Rating
1 | Enter your name, address, and contact details | Katrail Harris,IT Manager at Carmerek Labs. Address: 20 Ingram Street, Queens, New York. Email: katrail.harris@carmereklabs.com | Primary contact is the IT Manager; there is no dedicated security role (CISO/security lead). The contact email ("katrail.harris@") does not match the contact name ("Harris"); confirm the correct address before relying on it for incident and breach notifications. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | Low
2 | Describe the service that you provide to Carmerek | We provide a SaaS solution called "Carmerek X". This is a SaaS application used to provide Data Analysis service for Scientific Research purposes. | Horizon X is a SaaS data analysis platform used for scientific research. Note: the question refers to "Carmerek", but the service is provided to Carmerek's. Supplier criticality: HIGH, because Carmerek's research intellectual property is processed and stored in the application. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | Info
3 | Do you handle sensitive data? If yes, is the data encrypted? | The application handles confidential data. The data is intellectual property data that belongs to Carmerek. The database used in the backend is an Oracle Database. The database encrypts the data by default. | Confirms Carmerek Labs processes and stores Carmerek's confidential IP. Claim that the Oracle database "encrypts by default" needs verification: on-premises Oracle requires Transparent Data Encryption (TDE) to be enabled. Answer does not cover encryption in transit (TLS), backup encryption, key management, or who can access the keys. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | Medium
4 | Does your organization follow a cyber security framework? | Carmerek Labs is a startup, we still don't follow cyber security frameworks | No security framework (e.g. ISO 27001, SOC 2, NIST CSF) and no independent attestation. Security controls are ad hoc, with no governance, policies or assurance that they operate consistently. Being a startup does not reduce the risk to Carmerek's data. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | High
5 | Do you have a vulnerability management program in place? | We don't have a vulnerability scanner but we install regular updates to our windows servers | No vulnerability scanning. Patching is limited to Windows servers; the Carmerek X application, Oracle database, third-party libraries and network devices are not covered. Exploitable vulnerabilities could go undetected in an internet-facing application holding Carmerek's IP. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | High
6 | Do you undertake regular enterprise wide penetration testing? When was the last penetration test conducted? | We haven't done a penetration test yet, but we are plan to run one in the future. | The internet-facing SaaS application has never been penetration tested. No independent validation that the application and its tenant separation can withstand attack. | Evidence provided by Horizon Labs; reviewed and accepted as sufficient. | High
7 | Describe how your organization handles security detection and monitoring | Our IT team deals with all IT issues | "IT team deals with all IT issues" indicates no security monitoring, centralized logging, SIEM or alerting. A breach of Carmerek's data could go undetected for a long period. | Evidence provided by Horizon Labs; reviewed and accepted as sufficient. | High
8 | Describe your incident response capability | The IT team manages all incidents | No documented incident response plan, roles, or playbooks, and no commitment to notify Carmerek's of a breach within a defined time frame. This affects Carmerek's own regulatory notification obligations. | Evidence provided by Horizon Labs; reviewed and accepted as sufficient. | High
9 | Do you utilize Multi-factor authentication? | Yes, we use Okta for two factor authentication | Positive control: MFA via Okta. Confirm MFA covers all users including administrators, database and remote/server access, and that phishing-resistant methods are used for privileged accounts. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | Low
10 | Do you employ role-based access control? | No | No role-based access control. Users likely have broad or individually granted access, so it cannot be shown who can access Carmerek's data. Combined with Q11–13, this is the most serious finding. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | Critical
11 | Is the principle of least privileges followed? | No | Least privilege is not followed. Staff and possibly service accounts have more access than needed, increasing the impact of a compromised account or malicious insider. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | Critical
12 | Do you implement Segregation of duties for critical application? | No | No segregation of duties for critical applications. The same individuals can develop, deploy, administer and access production data without independent checks, enabling undetected errors, fraud or data theft. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | High
13 | Do you conduct period user access reviews? | No | No periodic user access reviews. Leavers and role changes may retain access to Carmerek's data indefinitely; excessive access is never detected or removed. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | High
14 | Do you conduct regular user security education awareness training and educational campaigns? | We have a security training module that's mandatory for anyone who joins the company | Training only at onboarding. No annual refresher, phishing simulation or role-based training for developers and administrators. Awareness decays over time and phishing remains a leading breach vector. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | Medium
15 | Do you have Data Loss Protection (DLP) capability in place? | No, but we take regular backups | No DLP capability. Backups protect availability, not confidentiality, so they do not answer the question. Nothing prevents or detects Carmerek's IP being copied, emailed or uploaded outside Carmerek Labs. Backup encryption, location and restore testing were also not described. | Evidence provided by Carmerek Labs; reviewed and accepted as sufficient. | High
Assessor: Information Security / GRC, on behalf of Carmerek's ¦ Date: 28 October 2026 ¦ Overall supplier risk: HIGH (see "Executive Risk Summary" tab)